## Overview
PropLink UK — Sprint Progress Tracker
Status values: Complete / In progress / Code-complete (blocked) / Not started / Deferred
Remarks = build-side notes. Comments = human notes, decisions, risks.
Sprint | Focus | Status | Remarks | Comments
Sprint 1 | Foundation & Core Infrastructure | Complete | All 6 tasks done and verified (23 unit + 12 E2E tests green). DB live on Supabase. Vercel/CI deploy criteria deferred per ADR-004. | Google OAuth deferred until H1.6.
Sprint 2 | Agent Portal & Listing Engine | In progress | Build underway on branch sprint-2 (Task 2.1 first). S3 + geocoding consumed via mockable service interfaces until H1.4/H2.1/H2.2. | Demo target: full agent journey.
Sprint 3 | Search, Map & Commute | Not started | SearchService, search UI, map & density grid, commute engine, saved searches & alerts. | Needs H3.1 (Maps keys + quotas); cache all Maps calls via Redis.
Sprint 4 | Investor Portal, KYC & Syndicates (EOI) | Not started | KYC (Sumsub + mock), pledge flow, refurb console, investor dashboard, lifecycle. | EOI only — no real money; KYC gate server-side. Needs H4.1, H4.2.
Sprint 5 | AI, Stripe & Buyer Portal | Not started | AiService, Advisor, AVM, Listing Enhancer, planning tool, Stripe billing, buyer portal. | Stripe for agent subs/boosts only; RICS disclaimer on all AI output. Needs H5.1, H5.3.
Sprint 6 | Intelligence, Hardening & Launch | Not started | Market intel, planning feed, ecosystem & ads, performance, security/GDPR closeout, QA/UAT, launch. | H6.2 pen test has long lead time — book early. Never cut security/KYC/GDPR.

## Sprint 1
Sprint 1 — Foundation & Core Infrastructure — COMPLETE
Definition of Done (PASSED): all 4 roles register/login with RBAC enforced; design system + live metrics strip; admin shell + audit; GDPR basics. Vercel/CI criteria deferred (ADR-004).
Human tasks: H1.1–H1.10 (H1.2 done; several deferred per ADR-004 — see Human Tasks sheet).
Task | Deliverables | Status | Remarks | Comments
1.1 Project setup | Next.js 16 + TS strict + Tailwind tokens, ESLint/Prettier, repo structure, .env.example, CI workflow, Sentry init | Complete | CI runs on first push (H1.1).
1.2 Database & Prisma | Full schema, PostGIS/pg_trgm migration, FTS trigger, seed (4 users + 3 agent profiles) | Complete | Verified on Supabase: migrate + seed clean; ST_DWithin + FTS pass.
1.3 Auth & RBAC part 1 | Credentials + Google providers, registration with role select, JWT carries role + kycStatus, login/logout | Complete | Register + login verified live. | Google provider deferred (H1.6).
1.4 Auth & RBAC part 2 | Email verify, password reset, route middleware, requireRole()/requireKyc(), GDPR endpoints | Complete | E2E: verify→login ×3 roles, 403, erasure. | Mock mailer until H1.7.
1.5 Layout & metrics strip | Global nav, KYC pill, metrics strip (Redis-cached), UI primitives, /dev/ui | Complete | /dev/ui + live strip E2E green. | No-cache fallback until H1.5.
1.6 Admin shell | /admin users table, placeholder tabs, AuditLog on mutations | Complete | Deactivate + audit row E2E green.

## Sprint 2
Sprint 2 — Agent Portal & Listing Engine — IN PROGRESS
Sprint goal: agents create rich distressed listings; admin approves; public detail page v1.
Definition of Done: full agent journey (create → approve → live → enquiry) passes E2E; 40 seeded listings browsable.
Human tasks: H2.1 S3 CORS · H2.2 Geocoding key · H2.3 Brand assets · H2.4 Beta-agent recruitment.
Task | Deliverables | Status | Remarks | Comments
2.1 S3 upload service | Presigned-POST endpoint (auth, type/size validation: images ≤10MB, PDFs ≤20MB), CloudFront URLs, ImageUploader (max 20) with drag-drop/previews/sort, CORS JSON for H2.1 | In progress | Storage behind service interface; local mock until H1.4/H2.1.
2.2 Multi-step listing form | 5 steps: address + geocode (Redis-cached), details (price in pence, ROI %), 8 distress tags + safeguard checkbox, media (photos, EPC cert + rating, floor plan), review → draft/submit. Status flow DRAFT→PENDING_REVIEW→LIVE→UNDER_OFFER→SOLD; listingLimit enforced (free tier: 3 live) | Not started | Geocoder mocked until H2.2. | Only admin can approve to LIVE.
2.3 Admin moderation queue | /admin/moderation: pending listings with preview; Approve (→LIVE + publishedAt + notify) / Reject (reason required → back to DRAFT, emailed via Resend) | Not started | Mock mailer until H1.7.
2.4 Agent profile & credibility hub | Public /agents/[id]: agency info, star rating (avg Appraisals), Verified Completed Deals counter, compliance code, Case Studies CRUD, qualified-only Investor Appraisals; multi-profile switching | Not started | Appraisal eligibility server-enforced.
2.5 Property detail page v1 | /marketplace/[id] SSR + SEO/OpenGraph: gallery, distress chips, EPC badge, price, ROI, static map pin, satellite embed, agent card, Post Enquiry form (→ Enquiry + email). Placeholders: comparables, price history | Not started | Target Lighthouse SEO ≥ 90.
2.6 Agent leads & analytics v1 | /agent/leads: enquiries across agent's listings with status management; view counter (session-deduped) + saves count | Not started
2.7 Seed data | 40 realistic distressed listings across UK cities (varied tags, EPC, £45k–£450k, real-ish postcodes with lat/lng), 3 case studies, 5 appraisals | Not started |  | Demo depends on this for browsable content.

## Sprint 3
Sprint 3 — Search, Map & Commute — NOT STARTED
Definition of Done: buyer/investor finds a property by text, filters, map and commute time; Maps costs guarded by cache + quota; alerts flowing.
Human tasks: H3.1 Maps/Places/Routes APIs + browser key + quotas · H3.2 Vercel Cron check.
Task | Deliverables | Status | Remarks | Comments
3.1 SearchService | Interface-first SearchService.search(): FTS + trigram, price/EPC/region/type/beds/ROI/distress-tag filters, bbox or centre+radius (PostGIS), sort + pagination; live count endpoint | Not started | Unit tests per filter; p95 < 150ms target.
3.2 Search UI | /marketplace filter sidebar, text box, live count, PropertyCard grid, URL-synced shareable params | Not started
3.3 Map view & density grid | List/Map toggle, clustered markers with viewport refetch, postcode-district distress heatmap, lazy-loaded Maps script | Not started | JS map only on /marketplace; static maps elsewhere. | Needs H3.1.
3.4 Commute travel-time engine | Hub autocomplete, mode toggle, max-time slider; commuteFilter() capped ≤25 candidates, Redis-cached 7 days, daily quota guard with straight-line fallback | Not started | Routes API bills per element — cap requests.
3.5 Saved searches & alerts | Save property + /saved, saved searches with alerts, daily cron emails new matches (idempotent) | Not started | Needs H3.2 (cron availability).

## Sprint 4
Sprint 4 — Investor Portal, KYC & Syndicates (EOI) — NOT STARTED
Definition of Done: full investor journey — register → KYC → discover → pledge → track → completion accounting — zero real payments, server-enforced gates.
Human tasks: H4.1 Sumsub sandbox + webhook · H4.2 Pusher app · H4.3 FCA counsel (parallel, human-only).
Task | Deliverables | Status | Remarks | Comments
4.1 KycService | SumsubKycService + MockKycService, /investor/kyc WebSDK flow, optional CRN → Companies House lookup, signature-verified webhook → KycRecord + navbar pill via Pusher, requireKyc() on every pledge mutation | Not started | Mock auto-approves when keys absent. | Needs H4.1/H1.10.
4.2 Syndicate projects & pledge flow | Project creation on LIVE property, browsable OPEN projects with funding bar, pledge flow with live equity preview + EOI banner, SYNDICATE_PAYMENTS_ENABLED=false guard (throws), FUNDED transition + share snapshot, withdraw while OPEN | Not started | EOI wording placeholder until H4.3 counsel text. | No real money — non-negotiable.
4.3 Refurb progress console | Members-only dashboard: milestones CRUD + photos, capital & expense ledger with running totals, live updates via Pusher | Not started | Non-members 403.
4.4 Investor dashboard | /investor: KYC status card, active pledges + equity %, funding bars, portfolio totals, global metrics | Not started
4.5 Lifecycle to completion | FUNDED → IN_REFURB → LISTED → COMPLETED; SuccessFee logged, verified-deal count bumped, members notified; payout calculation displayed only | Not started | No payment executed (EOI).

## Sprint 5
Sprint 5 — AI, Stripe & Buyer Portal — NOT STARTED
Definition of Done: all 4 AI features live with cost guards; agents pay test-mode subscriptions; complete buyer journey on-platform.
Human tasks: H5.1 Stripe account + products + CLI · H5.2 Anthropic limits · H5.3 Pricing decisions.
Task | Deliverables | Status | Remarks | Comments
5.1 AiService foundations | Anthropic client, model router, Redis response cache (24h), per-user rate limit, monthly spend counter with hard stop | Not started | Budget breach → friendly 429.
5.2 AI Investment Advisor | /investor/ai-scout streaming chat with tool use over SearchService, suggested chips, prompt caching, RICS disclaimer under every response | Not started
5.3 AVM | Land Registry ingest → ComparableSale, getComparables(), AVM endpoint (estimate, post-rehab GDV, capex, confidence), detail-page valuation card + comparables table + disclaimer | Not started | Cached 7 days per property. | Replaces detail-page placeholder.
5.4 AI Listing Enhancer | 'Enhance with AI' in listing form: description generation, tag suggestions (agent confirms), quality score with hints | Not started | Structured JSON output.
5.5 Planning probability tool | /intel/planning-probability: probability band + reasoning, Zod-validated output, pre-app disclaimer | Not started
5.6 Stripe billing | Tiers STARTER/PRO/ELITE via Checkout + webhooks → listingLimit; Listing Boost one-off (ranks first); /admin/fees with CSV; customer portal | Not started | Test mode throughout build. | Needs H5.1 + H5.3 price decisions.
5.7 Buyer portal & deal flow | /buy search preset + affordability calculator + price history; buyer↔agent chat (Pusher); viewing booking; digital offer → Deal Tracker stepper to COMPLETED (+ SuccessFee) | Not started

## Sprint 6
Sprint 6 — Intelligence, Hardening & Launch — NOT STARTED
Definition of Done: production deployment serving real listings; every module live or explicitly deferred (premium AVM data, native mobile, real syndicate payments pending FCA).
Human tasks: H6.1 ICO registration · H6.2 Pen test booking (long lead) · H6.3 Final legal docs · H6.4 Workspace email · H6.5 Production cutover checklist.
Task | Deliverables | Status | Remarks | Comments
6.1 Market intelligence | EPC Register auto-fetch on listing creation; area intel: price history chart, district trends, EPC uplift model | Not started | Needs H1.10 EPC key.
6.2 Planning research feed | planning.data.gov.uk integration (cached 24h), detail-page + /intel/planning feeds, graceful no-data state | Not started
6.3 Ecosystem marketplace & ads | /ecosystem partner directory + click tracking + admin approval; ad slots with CPM/CPC counters, partner billing, /admin/ads | Not started | Cut-first scope: defer ad billing if time pressure.
6.4 Performance | next/image + blur placeholders, code splitting, Redis caching, CDN cache headers, DB index audit | Not started | Targets: Lighthouse ≥ 90; p95 API < 300ms.
6.5 Security & GDPR closeout | OWASP pass (headers, CSRF, Zod audit, IDOR sweep, rate limits, webhook signature audit), secrets/dependency scan, final legal content, data export endpoint, ICO number in footer, backup + restore drill | Not started | ZAP baseline: no High findings. | Never cut. External pen test per H6.2.
6.6 Full QA & UAT | Unit coverage ≥ 70% on services; Playwright suite across all journeys; responsive QA + PWA manifest; staging UAT with beta users | Not started |  | Needs beta users from H2.4.
6.7 Launch | Per-listing SEO/JSON-LD, sitemap/robots, production env + live keys, seed real partner listings, marketing page, analytics, rollback procedure | Not started | Sumsub prod keys if approved, else 'verification opening soon' gate. | Needs H6.5.

## Human Tasks
Human Tasks (manual work the build depends on)
Status: Done / Pending / Deferred (ADR-004 = local-only phase decision). Details in docs/HUMAN_TASKS.md.
ID | Sprint | Task | Status | Notes
H1.1 | Sprint 1 | GitHub + Vercel | Deferred (ADR-004) | CI ships in-repo; runs on first push.
H1.2 | Sprint 1 | Supabase project + connection strings | Done | Migrate + seed verified against live DB.
H1.3 | Sprint 1 | Domains | Deferred (ADR-004)
H1.4 | Sprint 1 | AWS S3 / CloudFront | Deferred (ADR-004) | Uploads mocked behind storage service interface.
H1.5 | Sprint 1 | Upstash Redis | Pending (optional) | Graceful no-cache / no-limit fallback in dev.
H1.6 | Sprint 1 | Google Cloud OAuth | Pending (optional) | Google login auto-disabled; credentials auth works.
H1.7 | Sprint 1 | Resend (email) | Pending (optional) | Console/mock mailer behind mailer interface.
H1.8 | Sprint 1 | Sentry | Deferred (ADR-004)
H1.9 | Sprint 1 | Anthropic API key | Pending | Needed by Sprint 5 (Task 5.1).
H1.10 | Sprint 1 | Long-lead applications: Sumsub, EPC key, Companies House key | Pending | Submit early — longest lead times.
H2.1 | Sprint 2 | S3 CORS for browser uploads | Pending | Task 2.1 outputs the exact CORS JSON to paste.
H2.2 | Sprint 2 | Geocoding API + server Maps key + budget | Pending | Geocoder mocked until key supplied.
H2.3 | Sprint 2 | Brand assets (logo, favicon, palette confirmation) | Pending | Placeholder wordmark used otherwise.
H2.4 | Sprint 2 | Beta-agent recruitment (ongoing) | Pending | Pre-launch needs ≥10 agents with live listings.
H3.1 | Sprint 3 | Maps JS / Places / Routes APIs + browser key + quotas | Pending | Add Routes API to server key; set daily caps.
H3.2 | Sprint 3 | Vercel Cron availability check | Pending | Cron config ships as code in Task 3.5.
H4.1 | Sprint 4 | Sumsub sandbox config + webhook | Pending | Blocks Task 4.1 live integration; mock covers dev.
H4.2 | Sprint 4 | Pusher app (cluster eu) | Pending
H4.3 | Sprint 4 | Engage FCA counsel | Pending | Human-only; supplies final EOI wording for pledge screen.
H5.1 | Sprint 5 | Stripe account, products, CLI webhook secret | Pending | Blocks Task 5.6.
H5.2 | Sprint 5 | Anthropic production limits + spend cap | Pending
H5.3 | Sprint 5 | Confirm pricing decisions (tiers, boost, success fee) | Pending | Communicate before Task 5.6 begins.
H6.1 | Sprint 6 | ICO registration | Pending | Registration number shown in footer + Privacy Policy.
H6.2 | Sprint 6 | Book CREST penetration test | Pending | Long lead time — book at sprint start or earlier.
H6.3 | Sprint 6 | Final Privacy Policy / ToS / Cookie Policy | Pending | Replaces placeholders on /privacy, /terms, /cookies.
H6.4 | Sprint 6 | Google Workspace (support@/admin@) | Pending
H6.5 | Sprint 6 | Production cutover checklist | Pending | Runs alongside Task 6.7 (launch).